## Dashboard
Ohio Nonprofit 90-Day Launch Tracker
Start Date | 2026-06-01
Metric | Value
Total Tasks | 90
Not Started | 90
In Progress | 0
Blocked | 0
Done | 0
Percent Done | 0%
High/Critical Open | 81
Due Next 7 Days | 8
How to use this tracker
1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting.
1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting.
1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting.
1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting.
1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting.
1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting.
1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting. | 1. Change the Start Date in cell B3. Target dates in the 90-Day Plan update automatically. 2. Assign owners and update Status every day. 3. Use Budget, Grant Pipeline, Donor Pipeline, Board Roster, Compliance Calendar, and Agent Reports as working tabs. 4. Save receipts, board minutes, policy approvals, grant documents, and donor acknowledgments in the matching document folders. 5. The board should review Dashboard, Budget, Compliance Calendar, and Program/Agent updates at every early-stage board meeting.

## 90-Day Plan
Day | Target Date | Phase | Category | Task | Owner | Status | Priority | Evidence / Done Means | Notes
1 | 2026-06-01 | Phase 1 - Foundation | Formation | Create launch folder system and save Phase 2 kit. | Founder | Not Started | Critical | Folder system created.
2 | 2026-06-02 | Phase 1 - Foundation | Formation | Draft mission, vision, values, and first program one-pager. | Founder | Not Started | Critical | Mission worksheet completed.
3 | 2026-06-03 | Phase 1 - Foundation | Program | Identify target beneficiaries and service geography. | Program Manager Agent | Not Started | High | Beneficiary profile written.
4 | 2026-06-04 | Phase 1 - Foundation | Formation | Create nonprofit name shortlist and check Ohio name availability. | Compliance Agent | Not Started | High | Name search notes saved.
5 | 2026-06-05 | Phase 1 - Foundation | Marketing | Check domain, email, and social availability for top names. | Marketing Agent | Not Started | Medium | Brand availability notes saved.
6 | 2026-06-06 | Phase 1 - Foundation | Board | Draft board skills matrix and ideal board seat list. | Board Support Agent | Not Started | High | Board matrix completed.
7 | 2026-06-07 | Phase 1 - Foundation | Board | List 20 board prospects and rank them. | Founder | Not Started | High | Prospect list created.
8 | 2026-06-08 | Phase 1 - Foundation | Board | Send first 5 board outreach messages. | Founder | Not Started | High | Outreach logged.
9 | 2026-06-09 | Phase 1 - Foundation | Board | Send second 5 board outreach messages. | Founder | Not Started | High | Outreach logged.
10 | 2026-06-10 | Phase 1 - Foundation | Board | Hold first board prospect conversation. | Founder | Not Started | High | Conversation notes saved.
11 | 2026-06-11 | Phase 1 - Foundation | Formation | Draft articles purpose clause and dissolution clause for review. | Compliance Agent | Not Started | Critical | Draft clauses created.
12 | 2026-06-12 | Phase 1 - Foundation | Formation | Select statutory agent candidate and confirm address. | Founder | Not Started | Critical | Agent confirmation saved.
13 | 2026-06-13 | Phase 1 - Foundation | Finance | Draft first-year budget skeleton. | Finance Agent | Not Started | High | Budget tab started.
14 | 2026-06-14 | Phase 1 - Foundation | Fundraising | Build founding donor prospect list of 50 names. | Donor Relations Agent | Not Started | High | Donor list started.
15 | 2026-06-15 | Phase 1 - Foundation | Board | Hold two more board prospect conversations. | Founder | Not Started | High | Notes saved.
16 | 2026-06-16 | Phase 1 - Foundation | Formation | Choose preferred nonprofit name and backup name. | Founder | Not Started | High | Name decision logged.
17 | 2026-06-17 | Phase 1 - Foundation | Formation | Prepare Ohio Form 532B data and attachments. | Compliance Agent | Not Started | Critical | Filing packet ready.
18 | 2026-06-18 | Phase 1 - Foundation | Formation | Review articles with attorney or qualified reviewer. | Founder | Not Started | Critical | Review comments resolved.
19 | 2026-06-19 | Phase 1 - Foundation | Board | Confirm initial directors and officer candidates. | Founder | Not Started | Critical | Initial board list confirmed.
20 | 2026-06-20 | Phase 1 - Foundation | IRS | Prepare EIN information checklist. | Finance Agent | Not Started | High | EIN checklist completed.
21 | 2026-06-21 | Phase 1 - Foundation | Formation | File Ohio articles when ready. | Founder | Not Started | Critical | Filing submitted.
22 | 2026-06-22 | Phase 1 - Foundation | Formation | Save filing receipt and approved articles. | Secretary | Not Started | Critical | Receipt/articles saved.
23 | 2026-06-23 | Phase 1 - Foundation | IRS | Apply for EIN after Ohio formation is accepted. | Founder | Not Started | Critical | EIN confirmation saved.
24 | 2026-06-24 | Phase 1 - Foundation | Board | Create first board meeting agenda. | Board Support Agent | Not Started | High | Agenda drafted.
25 | 2026-06-25 | Phase 1 - Foundation | Governance | Draft bylaws/code of regulations for review. | Board Support Agent | Not Started | Critical | Bylaws draft ready.
26 | 2026-06-26 | Phase 1 - Foundation | Governance | Draft conflict of interest and financial controls policy. | Compliance Agent | Not Started | Critical | Policies drafted.
27 | 2026-06-27 | Phase 1 - Foundation | Finance | Draft banking resolution and officer slate. | Treasurer | Not Started | High | Resolution drafted.
28 | 2026-06-28 | Phase 1 - Foundation | Board | Send first board packet to directors. | Secretary | Not Started | High | Packet sent.
29 | 2026-06-29 | Phase 1 - Foundation | Board | Prepare board meeting folder and signature pages. | Secretary | Not Started | High | Folder complete.
30 | 2026-06-30 | Phase 1 - Foundation | Board | Hold or schedule first board meeting. | Board Chair | Not Started | Critical | Meeting held or scheduled.
31 | 2026-07-01 | Phase 2 - Governance & Infrastructure | Board | Finalize first board meeting minutes. | Secretary | Not Started | Critical | Minutes signed/stored.
32 | 2026-07-02 | Phase 2 - Governance & Infrastructure | Governance | Adopt bylaws/code of regulations. | Board Chair | Not Started | Critical | Board approval documented.
33 | 2026-07-03 | Phase 2 - Governance & Infrastructure | Governance | Adopt conflict of interest policy. | Board Chair | Not Started | Critical | Policy approved.
34 | 2026-07-04 | Phase 2 - Governance & Infrastructure | Governance | Collect annual conflict disclosures. | Secretary | Not Started | Critical | Disclosures stored.
35 | 2026-07-05 | Phase 2 - Governance & Infrastructure | Finance | Adopt financial controls policy. | Treasurer | Not Started | Critical | Policy approved.
36 | 2026-07-06 | Phase 2 - Governance & Infrastructure | Finance | Open nonprofit operating checking account. | Treasurer | Not Started | Critical | Account live.
37 | 2026-07-07 | Phase 2 - Governance & Infrastructure | Finance | Set up reserve savings plan or reserve account. | Treasurer | Not Started | High | Reserve method approved.
38 | 2026-07-08 | Phase 2 - Governance & Infrastructure | Finance | Create receipt capture system. | Finance Agent | Not Started | High | Receipt folder/app live.
39 | 2026-07-09 | Phase 2 - Governance & Infrastructure | Finance | Create chart of accounts and classes/projects. | Finance Agent | Not Started | High | Accounting structure ready.
40 | 2026-07-10 | Phase 2 - Governance & Infrastructure | Finance | Enter startup budget into tracker/accounting system. | Finance Agent | Not Started | High | Budget entered.
41 | 2026-07-11 | Phase 2 - Governance & Infrastructure | Compliance | Create compliance calendar with IRS, Ohio AG, Ohio SOS, SAM deadlines. | Compliance Agent | Not Started | Critical | Calendar created.
42 | 2026-07-12 | Phase 2 - Governance & Infrastructure | Compliance | Begin Ohio Attorney General charitable registration review. | Compliance Agent | Not Started | Critical | Registration path confirmed.
43 | 2026-07-13 | Phase 2 - Governance & Infrastructure | Compliance | Prepare Ohio AG registration documents or exemption determination request. | Compliance Agent | Not Started | High | Registration packet ready.
44 | 2026-07-14 | Phase 2 - Governance & Infrastructure | IRS | Prepare IRS Form 1023-series readiness checklist. | Compliance Agent | Not Started | Critical | IRS checklist started.
45 | 2026-07-15 | Phase 2 - Governance & Infrastructure | IRS | Gather articles, bylaws, board list, budget, policies, and narrative for IRS package. | Compliance Agent | Not Started | Critical | IRS file built.
46 | 2026-07-16 | Phase 2 - Governance & Infrastructure | Insurance | Request general liability and D&O insurance quotes. | Compliance Agent | Not Started | High | Quotes requested.
47 | 2026-07-17 | Phase 2 - Governance & Infrastructure | Insurance | Prepare insurance comparison for board. | Compliance Agent | Not Started | Medium | Comparison table ready.
48 | 2026-07-18 | Phase 2 - Governance & Infrastructure | Program | Finalize first program service workflow. | Program Manager Agent | Not Started | High | Workflow approved.
49 | 2026-07-19 | Phase 2 - Governance & Infrastructure | Program | Create intake form and service log. | Program Manager Agent | Not Started | High | Forms ready.
50 | 2026-07-20 | Phase 2 - Governance & Infrastructure | Volunteers | Create volunteer application and confidentiality agreement. | Volunteer Coordinator Agent | Not Started | High | Volunteer packet ready.
51 | 2026-07-21 | Phase 2 - Governance & Infrastructure | Volunteers | Write 3 volunteer role descriptions. | Volunteer Coordinator Agent | Not Started | Medium | Roles drafted.
52 | 2026-07-22 | Phase 2 - Governance & Infrastructure | Program | Identify 10 partner organizations. | Program Manager Agent | Not Started | High | Partner list built.
53 | 2026-07-23 | Phase 2 - Governance & Infrastructure | Program | Schedule first 3 partner meetings. | Founder | Not Started | High | Meetings on calendar.
54 | 2026-07-24 | Phase 2 - Governance & Infrastructure | Fundraising | Create donation page or donation intake process. | Donor Relations Agent | Not Started | High | Giving method live.
55 | 2026-07-25 | Phase 2 - Governance & Infrastructure | Fundraising | Create donor receipt/thank-you template. | Donor Relations Agent | Not Started | Critical | Receipt template ready.
56 | 2026-07-26 | Phase 2 - Governance & Infrastructure | Fundraising | Segment founding donor list by ask amount. | Donor Relations Agent | Not Started | High | Donor segments complete.
57 | 2026-07-27 | Phase 2 - Governance & Infrastructure | Marketing | Draft one-page nonprofit overview. | Marketing Agent | Not Started | High | One-pager ready.
58 | 2026-07-28 | Phase 2 - Governance & Infrastructure | Marketing | Draft simple website landing page copy. | Marketing Agent | Not Started | Medium | Copy ready.
59 | 2026-07-29 | Phase 2 - Governance & Infrastructure | Grants | Build grant readiness folder. | Grant Writing Agent | Not Started | High | Folder complete.
60 | 2026-07-30 | Phase 2 - Governance & Infrastructure | Grants | Research first 10 local grant prospects. | Grant Research Agent | Not Started | High | Grant pipeline started.
61 | 2026-07-31 | Phase 3 - Funding & Pilot | Fundraising | Launch founding donor campaign to first 25 prospects. | Donor Relations Agent | Not Started | Critical | 25 asks sent.
62 | 2026-08-01 | Phase 3 - Funding & Pilot | Fundraising | Follow up with top 10 founding donor prospects. | Founder | Not Started | High | Follow-ups logged.
63 | 2026-08-02 | Phase 3 - Funding & Pilot | Fundraising | Schedule 5 local business sponsor conversations. | Marketing Agent | Not Started | High | Sponsor meetings scheduled.
64 | 2026-08-03 | Phase 3 - Funding & Pilot | Fundraising | Prepare sponsor one-page package. | Marketing Agent | Not Started | High | Sponsor package ready.
65 | 2026-08-04 | Phase 3 - Funding & Pilot | Grants | Select best first grant or letter of inquiry target. | Grant Research Agent | Not Started | High | Best-fit target selected.
66 | 2026-08-05 | Phase 3 - Funding & Pilot | Grants | Draft first grant/LOI narrative. | Grant Writing Agent | Not Started | High | Draft ready.
67 | 2026-08-06 | Phase 3 - Funding & Pilot | Grants | Prepare program budget for grant/LOI. | Finance Agent | Not Started | High | Budget ready.
68 | 2026-08-07 | Phase 3 - Funding & Pilot | Grants | Submit first small grant or LOI if eligible. | Grant Writing Agent | Not Started | High | Submission logged.
69 | 2026-08-08 | Phase 3 - Funding & Pilot | Program | Confirm pilot program scope and date. | Program Manager Agent | Not Started | Critical | Pilot date set.
70 | 2026-08-09 | Phase 3 - Funding & Pilot | Volunteers | Recruit first 10 volunteers. | Volunteer Coordinator Agent | Not Started | High | Volunteer list ready.
71 | 2026-08-10 | Phase 3 - Funding & Pilot | Volunteers | Train first volunteer group. | Volunteer Coordinator Agent | Not Started | High | Training completed.
72 | 2026-08-11 | Phase 3 - Funding & Pilot | Program | Run pilot intake/rehearsal. | Program Manager Agent | Not Started | Medium | Dry run complete.
73 | 2026-08-12 | Phase 3 - Funding & Pilot | Program | Hold first pilot service activity. | Program Manager Agent | Not Started | Critical | Pilot delivered.
74 | 2026-08-13 | Phase 3 - Funding & Pilot | Program | Collect service logs, expenses, and feedback. | Program Manager Agent | Not Started | Critical | Pilot records complete.
75 | 2026-08-14 | Phase 3 - Funding & Pilot | Finance | Review pilot expenses against budget. | Finance Agent | Not Started | High | Variance notes saved.
76 | 2026-08-15 | Phase 3 - Funding & Pilot | Donors | Send donor thank-you messages and receipts. | Donor Relations Agent | Not Started | Critical | Receipts sent.
77 | 2026-08-16 | Phase 3 - Funding & Pilot | Marketing | Create impact update without violating privacy. | Marketing Agent | Not Started | High | Impact update drafted.
78 | 2026-08-17 | Phase 3 - Funding & Pilot | Board | Prepare 90-day board report. | Board Support Agent | Not Started | High | Board report drafted.
79 | 2026-08-18 | Phase 3 - Funding & Pilot | Finance | Prepare cash, budget, and restricted funds report. | Treasurer | Not Started | High | Finance packet ready.
80 | 2026-08-19 | Phase 3 - Funding & Pilot | Compliance | Review compliance calendar and missing filings. | Compliance Agent | Not Started | High | Compliance status updated.
81 | 2026-08-20 | Phase 3 - Funding & Pilot | Grants | Update grant pipeline and next deadlines. | Grant Research Agent | Not Started | Medium | Pipeline current.
82 | 2026-08-21 | Phase 3 - Funding & Pilot | Fundraising | Update donor pipeline and next asks. | Donor Relations Agent | Not Started | High | Pipeline current.
83 | 2026-08-22 | Phase 3 - Funding & Pilot | Program | Summarize pilot results and lessons learned. | Program Manager Agent | Not Started | High | Pilot memo complete.
84 | 2026-08-23 | Phase 3 - Funding & Pilot | Board | Hold board review meeting. | Board Chair | Not Started | Critical | Minutes and action items saved.
85 | 2026-08-24 | Phase 3 - Funding & Pilot | Operations | Approve next 90-day priorities. | Board Chair | Not Started | Critical | Quarter 2 priorities approved.
86 | 2026-08-25 | Phase 3 - Funding & Pilot | Agents | Reset agent weekly reporting rhythm. | Executive Director Agent | Not Started | Medium | Reports scheduled.
87 | 2026-08-26 | Phase 3 - Funding & Pilot | Fundraising | Plan next campaign or community event. | Donor Relations Agent | Not Started | Medium | Event/campaign outline ready.
88 | 2026-08-27 | Phase 3 - Funding & Pilot | Program | Decide whether to repeat, scale, or revise pilot. | Program Manager Agent | Not Started | High | Decision logged.
89 | 2026-08-28 | Phase 3 - Funding & Pilot | Compliance | Confirm all documents are stored in correct folders. | Compliance Agent | Not Started | High | Document audit complete.
90 | 2026-08-29 | Phase 3 - Funding & Pilot | Operations | Publish internal launch lessons and next steps. | Executive Director Agent | Not Started | Medium | Launch summary complete.
Formulas:
Target Date = Dashboard!$B3+[Day]-1

## Budget
First-Year Startup Budget Template
Category | Description | Budget | Actual | Variance | Restricted? | Owner | Notes
Startup legal/filing | Ohio filing, legal review, IRS user fee, charitable registration. | 2500 | 0 | 2500 | No | Compliance Agent
Accounting/bookkeeping | Accounting software, bookkeeping setup, CPA review. | 3000 | 0 | 3000 | No | Finance Agent
Insurance | General liability, D&O, cyber/event/auto as needed. | 2500 | 0 | 2500 | No | Compliance Agent
Website/email/tech | Domain, website, email, donor CRM, cloud storage, project management. | 1800 | 0 | 1800 | No | Marketing Agent
Marketing/outreach | Logo, flyers, printing, launch materials. | 1500 | 0 | 1500 | No | Marketing Agent
Program supplies | Direct service supplies, kits, meals, workshop materials. | 8000 | 0 | 8000 | Maybe | Program Manager Agent
Facilities/events | Meeting or program space, launch event, rentals. | 3500 | 0 | 3500 | Maybe | Program Manager Agent
Staff/contractors | Bookkeeping, grant writing, program coordination, admin support. | 20000 | 0 | 20000 | Maybe | Founder
Fundraising costs | Donation platform, merchant fees, event materials. | 2500 | 0 | 2500 | No | Donor Relations Agent
Reserve | Emergency reserve target. | 10000 | 0 | 10000 | No | Treasurer
TOTAL |  | 55300 | 0 | 55300

## Grant Pipeline
Funder | Grant Name | Fit Score | Amount | Due Date | Status | Eligibility Notes | Attachments Needed | Owner | Next Step
Local community foundation | Community impact grant | 4 | 10000 |  | Research | Likely fit if mission aligns. | Articles, EIN, board list, budget, narrative. | Grant Research Agent | Confirm deadline.
Corporate giving program | Local sponsorship/grant | 3 | 5000 |  | Research | Requires local business alignment. | One-page summary, budget, IRS letter when received. | Grant Research Agent | Build contact list.
Veterans/community funder | Veteran/family support grant | 5 | 15000 |  | Research | Strong fit if serving veterans/military families. | Program design, outcomes, partner letters. | Grant Writing Agent | Draft program narrative.
City/county opportunity | Community services funding | 3 | 25000 |  | Research | May require established track record. | SAM/UEI may be required. | Compliance Agent | Check eligibility.
Faith/community partner | Mission support grant | 4 | 3000 |  | Research | Good early relationship target. | One-page summary and budget. | Donor Relations Agent | Schedule meeting.
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research
Research

## Donor Pipeline
Donor / Sponsor | Segment | Ask Amount | Stage | Last Contact | Next Contact | Owner | Notes
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent
| Founding Donor |  | Prospect |  |  | Donor Relations Agent

## Board Roster
Name | Role | Committee | Term Start | Term End | Conflict Disclosure On File? | Giving/Pledge | Notes
| Board Chair | Executive/Governance |  |  | No
| Vice Chair | Executive/Fundraising |  |  | No
| Secretary | Executive/Governance |  |  | No
| Treasurer | Executive/Finance |  |  | No
| Director | Program |  |  | No
| Director | Fundraising |  |  | No
| Director | Community |  |  | No

## Compliance Calendar
Frequency | Deadline/Event | Owner | Target Date | Status | Notes
Once | File Ohio Articles of Incorporation | Founder |  | Not Started | Use current Ohio Secretary of State form/portal.
Once | Apply for EIN | Founder |  | Not Started | Apply through IRS after formation.
Once | First board meeting | Board Chair |  | Not Started | Adopt bylaws, policies, officers, bank authority.
Once/as required | IRS Form 1023-series application | Compliance Agent |  | Not Started | Submit electronically through Pay.gov with user fee.
Once/as required | Ohio Attorney General charitable registration | Compliance Agent |  | Not Started | Verify requirement/exemption through Charitable Ohio system.
Monthly | Bank reconciliation and finance report | Treasurer |  | Not Started | Review by board/finance committee.
Quarterly | Board meeting | Board Chair |  | Not Started | Monthly recommended during first year.
Annually | Conflict of interest disclosures | Secretary |  | Not Started | Collect from directors/officers/key staff.
Annually | Budget approval | Treasurer |  | Not Started | Approve before fiscal year if possible.
Annually | IRS Form 990-series return | Treasurer/CPA |  | Not Started | Generally 15th day of 5th month after fiscal year-end.
Annually | Ohio AG annual report | Compliance Agent |  | Not Started | Generally due with IRS timing; Ohio honors IRS extension.
Every 365 days if SAM registered | SAM.gov renewal | Grant Research Agent |  | Not Started | Required to keep federal registration active.
Every 5 years if no other Ohio business filing | Ohio Statement of Continued Existence | Secretary |  | Not Started | Due in six-month window prior to expiration.
As needed | Professional solicitor review | Compliance Agent |  | Not Started | If hiring paid outside solicitors.
As needed | Payroll filings | Treasurer/Payroll provider |  | Not Started | If employees are hired.
As needed | Insurance renewals | Compliance Agent |  | Not Started | Track expiration dates.

## Agent Reports
Week Ending | Agent | Top 3 Completed Tasks | Blocked Items | Decisions Needed | Next Week Top 3 | Documents Created/Updated
Executive Director Agent
Compliance Agent
Finance Agent
Grant Research Agent
Grant Writing Agent
Donor Relations Agent
Volunteer Coordinator Agent
Program Manager Agent
Marketing Agent
Board Support Agent

## Source Links
Official Source | URL | Use in Tracker
Ohio Secretary of State - Business Filing Forms and Fee Schedule | https://www.ohiosos.gov/business/business-filing-forms | Ohio Form 532B and fee verification.
Ohio Secretary of State - Maintain Active Status | https://www.ohiosos.gov/business/keep-your-active-status | Statement of Continued Existence calendar.
Ohio Revised Code 1702.27 | https://codes.ohio.gov/ohio-revised-code/section-1702.27 | Board minimum director rule.
Ohio Attorney General - Charity Registration | https://charitable.ohioago.gov/Charity-Registration | Ohio charitable registration and annual report tracking.
Ohio Attorney General - Starting and Maintaining a Charity in Ohio | https://charitable.ohioago.gov/Charity-Registration/Starting-a-Charity-in-Ohio | Ohio charity filing workflow.
IRS - Application for Recognition of Exemption | https://www.irs.gov/charities-non-profits/application-for-recognition-of-exemption | Form 1023-series application tracking.
IRS - Annual Exempt Organization Return Due Date | https://www.irs.gov/charities-non-profits/annual-exempt-organization-return-due-date | Form 990 timing.
IRS - Written Acknowledgments | https://www.irs.gov/charities-non-profits/charitable-organizations/charitable-contributions-written-acknowledgments | Donor receipt requirements.
SAM.gov Entity Registration | https://sam.gov/entity-registration | Federal awards registration planning.
Grants.gov Organization Registration | https://www.grants.gov/applicants/applicant-registration/organization-registration | Federal grant registration timing.
eCFR 2 CFR Part 200 Subpart D | https://www.ecfr.gov/current/title-2/subtitle-A/chapter-II/part-200/subpart-D | Federal grant internal controls and monitoring.

## Lists
Status | Priority | Owner | Category
Not Started | Critical | Founder | Formation
In Progress | High | Board Chair | Governance
Blocked | Medium | Secretary | Finance
Done | Low | Treasurer | Compliance
|  | Executive Director Agent | Program
|  | Compliance Agent | Fundraising
|  | Finance Agent | Grants
|  | Grant Research Agent | Marketing
|  | Grant Writing Agent | Volunteers
|  | Donor Relations Agent | Board
|  | Volunteer Coordinator Agent | Agents
|  | Program Manager Agent | Operations
Marketing Agent
Board Support Agent